## Template
Appendix A PROJECT TIMELINE
| Project Title | Resilient Next Generation Transit Facility Plan | [10 empty] | Firm
|  | Fund Source | Fiscal Year 2019/20 | [11 empty] | FY 2020/21 | [11 empty] | FY 2021/22
Task Number |  | Responsible Party | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | Deliverable
1 | Project Administrative Tasks
1.1 | Contract with Caltrans | Project Manager | [36 empty] | Executed Restricted Grant Agreement | bar: Fiscal Year 2019/20 J
1.2 | Kick-off Meeting | Project Manager | [36 empty] | List of Action Items with responsible party | bar: Fiscal Year 2019/20 A
1.3 | Quarterly Invoicing & Reporting | Project & Finance Manager | [36 empty] | Quarterly Reports & Invoices | bar: Fiscal Year 2019/20 J; Fiscal Year 2019/20 A; FY 2020/21 J; FY 2020/21 O; FY 2020/21 J; FY 2020/21 A
1.4 | Procurement of Consultants | Transit & Project Manager | [36 empty] | RFP released and signed agreement with selected firm | bar: Fiscal Year 2019/20 S to Fiscal Year 2019/20 N
2 | Climate Vulnerability Assessment of Potential Facility Sites
2.1 | Define Facility Needs | Consultant, Project & Transit Manager | [36 empty] | List of minimum facility and site parameters for the new facility | bar: Fiscal Year 2019/20 D to Fiscal Year 2019/20 J
2.2 | Identify Potential Sites | Consultant & Transit Manager | [36 empty] | List of potential adequately sized and geographically located sites | bar: Fiscal Year 2019/20 J to Fiscal Year 2019/20 F
2.3 | Conduct Climate Vulnerability Assessment | Consultant & Project Manager | [36 empty] | List of risks and adaptation strategies by site | bar: Fiscal Year 2019/20 M to Fiscal Year 2019/20 A
2.4 | Working Paper #1 | Consultant & Project Manager | [36 empty] | Working Paper #1 | bar: Fiscal Year 2019/20 M
3 | Resilient Next Generation Transit Facility
3.1 | Conceptual Facility Design | Consultant | [36 empty] | Conceptual Facility Design | bar: Fiscal Year 2019/20 M to FY 2020/21 A
3.2 | Resilient Fueling Infrastructure | Consultant | [36 empty] | Analysis of Resilient Fueling Infrastructure Options | bar: Fiscal Year 2019/20 M to FY 2020/21 A
3.3 | Conceptual Site Design | Consultant | [36 empty] | Conceptual site designs for selected potential sites | bar: Fiscal Year 2019/20 M to FY 2020/21 A
3.4 | Working Paper #2 | Consultant & Project Manager | [36 empty] | Working Paper #2 | bar: FY 2020/21 A to FY 2020/21 S
3.4 | Public Outreach | Consultant | [36 empty] | Input from the public and elected officials | bar: FY 2020/21 O
4 | Cost Estimates and Implementation Recommendations
4.1 | Financial Plan | Consultant | [36 empty] | Consultant recommendations and cost estimates for Next Generation Transit Facility. | bar: FY 2020/21 O to FY 2020/21 N
4.2 | Draft and Final Plan Development & Presentation | Consultant, Project & Transit Manager | [36 empty] | Draft and final plan | bar: FY 2020/21 D to FY 2020/21 J
5 | Resilient Next Generation Transit Facility - Next Tasks after Grant Completion
5.1 | Identify/Budget Funds for Procurement of Property | Transit Manager | [36 empty] | Purchased property for facility | bar: FY 2020/21 M to FY 2020/21 M
5.2 | Initiation Environmental Analysis of Procured Property | Consultant & Transit Manager | [36 empty] | Completed environmental assessment | bar: FY 2021/22 J to FY 2021/22 A
5.3 | Pursue Funding to Complete Design and Construction of the Resilient Next Generation Transit Facility | Consultant & Transit Manager | [36 empty] | Funding construct Resilient Next Generation Transit Facility | bar: FY 2021/22 O to FY 2021/22 J
TOTALS
Yuba-Sutter Transit Responsibility | bar: Fiscal Year 2019/20 J
Consultant Responsibility | bar: Fiscal Year 2019/20 J
Instructions: The blue indidcates Yuba-Sutter Transit's ideal schedule. Modify this schedule as needed to reflect accureate completion dates for each task based on your firm's time and resources available.